## Overview
DATA FOR DASHBOARD
IMPACT |  | OPERATIONS
Objectives | % Complete | Activities | % Complete
Maintain & Improve Programs | 6.25% | Invest in Information Technology Upgrades | 0%
Evaluate Program Outcomes | 12.5% | Improve Internal Communications | 25%
REVENUE |  | BRAND
Activities | % Complete | Activities | % Complete
Increase Contributed Revenue by 10% | 8.333% | Streamline Organizational Messaging | 0%
Assess Feasibility of Social Enterprise | 35%
Update Financial Systems | 0%
Strategic Plan
Dashboard Overview

## Impact
IMPACT DASHBOARD
Objectives | Activities | Deadline | % Complete | Owner | Status Commentary
Maintain and Improve Current Progams | Work with operations and finance to determine criteria and timing for future program expansion | 2014-10-15 | 25% | Chief Program Officer | In progress
| Develop process improvement plan for current programs including internal referrals and case conferencing | 2014-12-15 | 0% | Program Manager | Initial meeting set for 9/20/14
| Communicate plan to all staff | 2015-01-10 | 0% | Program Manager
| Routinely evaluate impact of process improvement changes to ensure positive impact on clients and organization | Quarterly | 0% | Program Manager
Evaluate Program Outcomes | Update organizational theory of change and logic model | 2014-10-30 | 50% | Program Evaluator
| Develop and deploy evaluation plan | 2014-11-30 | 0% | Program Evaluator
| Analyze evaluation findings | Annually | 0% | Program Evaluator
| Communicate evaluation findings to staff, Board and constituents | Annually | 0% | Communications Manager

## Revenue
REVENUE DASHBOARD
Objectives | Activities | Deadline | % Complete | Owner | Status Commentary
Increase Contributed Revenue by 10% | Diversify funding sources by hiring an additional development staff member to increase individual, unrestricted gifts to $600,000 annually | 2015-01-15 | 25% | Dev't Director | Job description complete
| Identify and meet with 50 current donors with interest and capacity to increase giving | 2015-05-30 | 0% | Dev't Director/ CEO | 10 donors meetings/month
| Conduct feasibility study to launch a capital campaign in 2016 | 2015-03-01 | 0% | Dev't Director
Assess Feasibility of Social Enterprise | Engage consultant to help with feasibility assessment for an earned-income social enterprise to support ongoing programming and overhead | 2014-10-20 | 75% | Dev't Director/ COO | Top 2 candidates selected
| Set social enterprise objectives and selection criteria | 2014-10-20 | 100% | Dev't Director
| Conduct initial opportunity assessment for social enterprise | 2015-01-01 | 0% | Dev't Director
| Determine top 1-2 social enterprises | 2015-02-15 | 0% | Dev't Director
| Seek Board approval for social enterprise investments | 2015-03-01 | 0% | Dev't Director/ COO
Update Financial Systems | Ensure financial systems and controls are in line with best practices | 2015-01-01 | 0% | CFO
| Assess organizational needs for financial software | 2014-11-20 | 0% | CFO
| Research financial management software that meets organization's needs | 2015-01-15 | 0% | Financial Manager
| Select financial management software | 2015-04-30 | 0% | Financial Manager

## Operations
OPERATIONS DASHBOARD
Objectives | Activities | Deadline | % Complete | Owner | Status Commentary
Invest in Information Technology Upgrades | Conduct information technology assessment to ensure staff needs are met | 2015-03-15 | 0% | IT Manager
| Research available technology that can meet needs identified in the assessment | 2015-04-20 | 0% | IT Manager
| Coordinate with fund development to raise funds needed to make upgrade investments | 2015-04-20 | 0% | IT Manager
| Develop staff training for new technology, if needed | 2015-07-01 | 0% | IT Manager
| Begin information technology upgrades | 2015-07-15 | 0% | IT Manager
Improve Internal Communications | Assemble cross-divisional staff committee to determine internal communication priorities | 2014-09-30 | 100% | HR Manager
| Develop ideas to address internal communication issues | 2014-10-30 | 25% | HR Manager | Initial meeting complete
| Solicit broader staff input on potential changes | 2014-11-15 | 0%
| Incorporate staff feedback and roll out internal communication improvement(s) | 2014-12-01 | 0%
| Monitor the progress of improvements and adjust as needed | Ongoing | 0%

## Brand
BRAND DASHBOARD
Objectives | Activities | Deadline | % Complete | Owner | Status Commentary
Streamline Organizational Messaging | Develop organization's value proposition in the community | 2015-01-30 | 0% | Marketing Manager
| Develop key marketing messages to various constituencies | 2015-03-30 | 0% | Marketing Manager
| Develop marketing strategy | 2015-07-01 | 0% | Marketing Manager
| Solicit executive team input on marketing strategy and messages | 2015-07-30 | 0% | Marketing Manager
| Deploy marketing strategy to all staff and Board members | 2015-09-01 | 0% | Marketing Manager
| Assess effectiveness of marketing strategy | 2015-12-30 | 0% | Marketing Manager